## Sheet1
A38 / A30 Bodmin
Item | Plant, Labour and Materials Requirements | Nr | UNIT | RATE | TOTAL
Advanced Signage
Site
| 2 * operatives ( 1 driver 1 non-driver ) | 1 | Day
| 1 * 3.5 tonne traffic management vehicle | 1 | Day
| Fuel |  | P/Mile
| 2* P7003 Advanced signage (charge as large hired over 22 wks) | 2 | No P/Wk
| 2* WBM frames | 2 | No P/Wk
| Sand Bags | 20 | No
Design of Traffic Management
| Design traffic management layouts |  | No | 180
Prep and install the site
| 1 * 20 Tonne TM Vehicle | 1 | Shift
| 1 * IPV Including Driver | 3 | Shift
| 20 Tonne Traffic Management Vehicle | 3 | Shift
| 2 * 12b operatives and 1* training operative (3 opps in total) | 3 | Shift
| Fuel |  | P/Mile
Initial Phase 1Set Up Equipment
| P7004 Advanced Sign (Large) | 4 | No P/Wk
| P7005 Advanced Sign (Large) | 4 | No P/Wk
| WBM Frames ( Large) | 12 | No P/Wk
| Frames | 66 | No P/Wk
| Signs | 50 | No P/Wk
| Sand Bags (6 per frame) | 396 | Sale
| Lamps | 65 | No P/Wk
| Cones (@ 4.5 centres) | 150 | No P/Wk
| Sign Lamps |  | No P/Wk
| HI Lamps | 3 | No P/Wk
| Safety Rope | 2 | No P/Wk
| Safety Cones (@ 9 Centres) | 20 | No P/Wk
| P7006.1 Sorry for Delay (Large) | 4 | No P/Wk
| P7006.1 HA Hail (Large) | 4 | No P/Wk
| P Man @ Work End + Dereg ( Large) | 8 | No P/Wk
30mph System
| Advanced Warning (Large) | 4 | No P/Wk
| Signs | 8 | No P/Wk
| Frames | 18 | No P/Wk
| Sand Bags (6 per frame) | 108 | Sale
| Signs Repeaters ( Small) | 6 | No P/Wk
All to be hired over a 22 week period please give a price per week
Works Access and Works Egress
| Signs | 3 | No P/Wk
| Frames | 3 | No P/Wk
| Sandbags | 12 | Sale
Prep the road closure and diversion to Turfdown Road
| 7.5 Tonne Traffic Management Vehicle | 2 | Shift
| 2 * 12b operatives and 1* training operative (3 opps in total) | 2 | Shift
| Fuel |  | P/Mile
Temporary Traffic Signals
| 4 Phase Silent Running System | 1 | P/Wk
| Traffic Signals Ahead | 4 | P/Shift
| When Red Light Show Wait Here | 4 | P/Shift
| RCCPs | 6 | P/Shift
| Sand Bags | 32 | Sale
Turfdown Road Closure and Diversion
Advanced Signage
| 2 * operatives ( 1 driver 1 non-driver ) | 1 | Day
| 1 * 3.5 tonne traffic management vehicle | 1 | Day
| Fuel |  | P/Mile
| 2* Advanced signage ( charge as large for hire over 2 wks) | 2 | No P/Wk
| Frames | 2 | No P/Wk
| Sand Bags | 20 | No
| Additional Dates for next weekends closure | 1 | Sale
| Signs | 67 | No P/Wk
| Frames | 67 | No P/Wk
| Sand Bags (4 per frame) | 268 | Sale
| Cones | 20 | No/P/WK
| Lamps | 10 | No/P/WK
All to be hired over a 2 week period please give a price per week
Install Maintain and Dismantle Turfdown Road Closure And Diversion
| 2 * 12a Operative (days & nights) | 4 | Per Shift
| 1 * 3.5 Tonne TM Vehicle | 4 | Per Shift
| Fuel |  | P/Mile
Clear Road Closure and diversion to Turfdown Road
| 7.5 Tonne Traffic Management Vehicle | 2 | Shift
| 2 * 12b operatives and 1* training operative (3 opps in total) | 2 | Shift
| Fuel |  | P/Mile
Prep the road closure and diversion to Lanhydrock Road
| 7.5 Tonne Traffic Management Vehicle | 1 | Shift
| 1 * 12b operatives and 1* training operative (2 opps in total) | 1 | Shift
| Fuel |  | P/Mile
Lanhydrock Road Closure and Diversion
Advanced Signage
| 2 * operatives ( 1 driver 1 non-driver ) | 1 | Day
| 1 * 3.5 tonne traffic management vehicle | 1 | Day
| Fuel |  | P/Mile
| Advanced signage (charge as large for hire over 1 wk) | 2 | No P/Wk
| Advanced signage on B3269/A30,A30 @ St Blazey & A390/A3082 (charge as large for hire over 1 wk) | 3 | No P/WK
| Frames | 5 | No P/WK
| Sand Bags | 20 | Sale
| Signs | 42 | No P/Wk
| Frames | 42 | No P/Wk
| Sand Bags (4 per frame) | 252 | Sale
| Cones | 20 | No/P/WK
| Lamps | 10 | No/P/WK
All to be hired over a 1 week period
Install maintain and dismantle Lanhydrock Road Closure And Diversion
| 2 * 12a Operative (days & nights) | 10 | Per Shift
| 1 * 3.5 Tonne TM Vehicle | 10 | Per Shift
| Fuel |  | P/Mile
Clear Road Closure and Diversion to Lanhydrock Road
| 7.5 Tonne Traffic Management Vehicle | 1 | Shift
| 1 * 12b operatives and 1* training operative (2 opps in total) | 1 | Shift
| Fuel |  | P/Mile
Prep the road closure and diversion to the A30 On-Slip Road
| 7.5 Tonne Traffic Management Vehicle | 1 | Shift
| 2 * 12b operatives and 1* training operative (3 opps in total) | 1 | Shift
| Fuel |  | P/Mile
A30 On-Slip Road Closure and Diversion
Advanced Signage
| 2 * operatives ( 1 driver 1 non-driver ) | 1 | Day
| 1 * 3.5 tonne traffic management vehicle | 1 | Day
| Fuel |  | P/Mile
| Advanced signage ( charge as large for hire over 1 wk) | 1 | No P/Wk
| Frames | 1 | No P/Wk
| Sand Bags | 10 | Sale
| Signs | 26 | No P/Wk
| Frames | 26 | No P/Wk
| Sand Bags (4 per frame) | 104 | Sale
| Cones | 20 | No/P/WK
| Lamps | 10 | No/P/WK
All to be hired over a 1 week period
Install, maintain and dismantle the A30 On-Slip Road Closure And Diversion
| 2 * 12a Operative (days & nights) | 1 | Per Shift
| 1 * 3.5 Tonne TM Vehicle | 1 | Per Shift
| Fuel |  | P/Mile
Clear Road Closure and Diversion to the A30 On-Slip Road
| 7.5 Tonne Traffic Management Vehicle | 2 | Shift
| 2 * 12b operatives and 1* training operative (3 opps in total) | 2 | Shift
| Fuel |  | P/Mile
Additional Visits For Switches Or Maintenance Visits
| 2 * 12a Operative (days & nights) | 1 | Per Shift
| 1 * 3.5 Tonne TM Vehicle | 1 | Per Shift
| Fuel |  | P/Mile
| Fuel |  | P/Mile
| Cone Sleeves |  | Each/Sale
| Battery |  | Each/Sale
Dismantle the site
| 1 * IPV Including Driver | 2 | Shift
| 20 Tonne Traffic Management Vehicle | 2 | Shift
| 2 * 12b operatives and 1* training operative | 2 | Shift
| Fuel |  | P/Mile